## Read Me
Portillo Roofing - Site Skeleton, Keyword & Schema Map (v3, council-reviewed)
2026-10-09 (v3.1: owner answers applied - founded 2025, 25+ yrs experience; testimonials not real; TXST = San Marcos). Reviewed by a 4-seat council (local SEO, AI search, owner economics, red team). Nothing on the website has been changed yet.
Start here
1. Phase 0 - Fix First: legal/accuracy problems on the LIVE site. These come before any new page.
2. Off-site Entity: the work that drives map-pack and AI answers more than pages do.
3. Page Map: the build list. Phase 1 = 25 pages (18 new, 7 existing reworked). Everything else is Planned, Section or Gated.
4. Council Log: what each reviewer said and what was adopted or overridden.
Legend
Yellow fill = you confirm or fill in (Offered?, Proof on hand, Completed jobs per town, min job size, Keyword Planner numbers, AI baseline results).
Status: Live = exists ¦ Draft = content exists, page not built ¦ Planned = build ¦ Section = a block on its parent page, not its own URL ¦ Gated = build ONLY once real proof exists.
Phase: 1 = first build ¦ 2 = next ¦ 3 = only when earned.
Proof on hand: Y / N / ?. A quoted or in-progress job is not proof.
Rules this map follows
One keyword cluster per page (checked automatically - no keyword is primary on one page and secondary on another).
No /areas/austin/: home owns 'roofing contractor austin'; each roofing service page owns '<service> austin'.
Town pages and Service x Town pages are gated on completed local jobs (Google scaled-content / doorway policies). Phase follows drive time from Dale.
Non-roofing trades live as sections on /remodeling/ or /countertops/ and get promoted to their own page when proof + search volume justify it.
Google stopped showing FAQ rich results in May 2026. FAQ text still matters (AI answers quote it); FAQ markup is optional.
Meta descriptions are blank on purpose - write each by hand from the Copy column. Templated metas were removed (duplicate-content signal).
Keyword Planner steps (about 15 min)
ads.google.com > Tools > Keyword Planner > 'Get search volume and forecasts' > paste Seed Keywords column A > Location: Austin-Round Rock-Georgetown metro (covers Travis, Williamson, Hays, Bastrop, Caldwell) > last 12 months > download CSV and send it back.
Without ad spend you get ranges ('10-100'); I'll convert to midpoints. 'Near me' and 'best ...' terms track demand only - they're won through GBP/reviews.

## Phase 0 - Fix First
# | Severity | Fix | Where | Why / source | Owner | Done?
1 | Critical | Remove competitor photos hotlinked through kimi-web-img.moonshot.cn and captioned as Portillo projects | main: index.html:75,182,247,266,273,280; services.html:71,96,142,284; about.html:71,119; contact.html:69 (relaunch branch already removes them) | Copyright + deceptive advertising; contradicts 'real project photos'. | Claude (hotfix branch, your approval)
2 | Critical | Remove the three testimonials (Sarah Johnson, Mike Rodriguez, Jennifer Chen) - owner confirmed NOT real | main: index.html ~300-336 | FTC 16 CFR 465 (fake reviews/testimonials), civil penalties per violation. | Claude Code
3 | Critical | Rewrite insurance copy: 'work directly with your insurance company to ensure you get fair coverage' + 'Direct insurance billing' | main services.html:254,260; relaunch services.html:319,325 | Tex. Ins. Code 4102.163: contractor may not act as or advertise as public adjuster; websites count as advertising (28 TAC 21.102). | Claude drafts, Marco approves
4 | Critical | Add deductible notice to quote/contract template for insurance-funded jobs >= $1,000 | quote system (generate_quote.js) | Bus. & Com. Code 27.02; illegal to waive/absorb deductible. | Claude (quote system)
5 | High | Use 'Founded 2025 - 25+ years of experience' everywhere; remove every '50+ years' and any '25+ years in business' wording (site, GBP, BBB, Yelp) | relaunch index.html / about.html | Owner confirmed: founded 2025, 25+ years experience. Conflicting facts get repeated by AI answers. | Claude Code (site) / Marco (profiles)
6 | High | Remove or source '1000+ roofs', '5-star rating', 'Lifetime warranty', 'Licensed' | relaunch index.html:100,104,170,262,366 | Texas has no state roofing license; unsourced numbers flow into schema/AI copy. | Marco confirm -> Claude
7 | High | Verify 'BBB Accredited' claim against live BBB profile | relaunch index.html:308,320 | Claim must be true. | Marco
8 | High | Merge relaunch branch (after the fixes above) | feature/crew-portfolio-update | Portfolio + cleaned pages are stuck unmerged since Aug 8. | Marco approves PR
9 | High | Render project pages as static HTML (not from portfolio-data.js) | portfolio.html / portfolio-data.js | Most AI crawlers don't run JavaScript. | Claude
10 | High | Set up Google Search Console + Bing Webmaster Tools; submit sitemap; IndexNow ping on Netlify deploy | DNS / Netlify | ChatGPT search leans on Bing's index; GSC needed to measure anything. | Marco (accounts) + Claude (config)
11 | Medium | robots.txt + sitemap.xml: allow Googlebot, Bingbot, OAI-SearchBot, ChatGPT-User, PerplexityBot | repo root | Allow search/answer crawlers; GPTBot / Google-Extended only govern training. | Claude
12 | Medium | Build check: fail deploy if output HTML contains '[', 'TODO' or 'placeholder' | repo build script | Stops placeholders like '[year]' shipping. | Claude
13 | Medium | Photo-consent line in quote template; builder OK before publishing GC jobs | quote system | Needed before project pages publish. | Claude (quote system)
14 | Low | noindex /thank-you/; 301 every old .html URL to its new folder URL | _redirects | Clean index; no broken links. | Claude

## Page Map
ID | Phase | Status | Surface | Path | Primary keyword (owns) | Secondary keywords | Intent | Title tag (draft) | Title len | H1 / H2 (draft) | Meta description (write by hand) | Meta len | Copy must include | Schema (JSON-LD) | Proof required before publishing | Proof on hand? | Index | Feeds (internal links) | Monthly searches | Notes
P001 | 1 | Live | Home | / | roofing contractor austin | roofing company austin; roofers austin tx; best roofing company austin | Commercial | Austin Roofing Contractor ¦ Portillo Roofing | 44 | Family-Owned Roofing Contractor for Austin & Central Texas |  |  | One location line used everywhere: 'Based in Dale, serving the Austin metro.' Facts line: 'Founded 2025 - 25+ years of roofing experience.' Never '25+ years in business' or '50+ years'. Real project photos only. No testimonials until real reviews exist. | RoofingContractor + GeneralContractor (#org): foundingDate, address (Dale), telephone, areaServed [14 cities w/ Wikipedia sameAs], sameAs [GBP, BBB, Yelp, Facebook], hasOfferCatalog; WebSite | Real photos; NAP; founding year (2025) | ? | index | All hubs, top roofing services, /projects/, /for-builders/ | 0 | 'best roofing company austin' is won by GBP/reviews/listicles, not a page - kept as a secondary here only. Fix Phase 0 items before anything else.
P002 | 1 | Live | Static | /about/ | family owned roofing company austin |  | Navigational | About Portillo Roofing - Family-Owned in Dale, TX | 49 | A Family Roofing Business, Built on the Roof |  |  | Founded 2025; 25+ years of hands-on roofing experience behind it (say whose); family history; crew (Arturo); real photos. | AboutPage + Person (Marco Portillo, Marco Sr.) | - | Y | index | /projects/, /contact/ | 0 | Live as about.html -> 301 to /about/.
P003 | 1 | Live | Static | /contact/ | portillo roofing contact |  | Navigational | Contact & Free Roof Inspection ¦ Portillo Roofing | 49 | Request a Free Roof Inspection |  |  | Phone (512) 629-1342, email, hours, service-area zones. | ContactPage | - | Y | index | /areas/, /services/ | 0 | Live as contact.html -> 301.
P004 | 1 | Planned | Static | /for-builders/ | roofing subcontractor austin |  | Commercial | Roofing Subcontractor for Builders & GCs ¦ Portillo Roofing | 59 | Roofing Subcontractor for Austin Builders & GCs |  |  | Capability sheet, not marketing: insurance (GL + workers' comp limits, COI on request); crew size + squares/week; lead time PO->start; systems (SnapLok, mechanical-lock, TPO, curved panels); references (Travis County, UT, TXST); supplier accounts / net terms / W-9 / lien waivers; one-field 'send plans for bid' form. | Service + BreadcrumbList | - | Y | index | /services/new-construction-roofing/, /services/commercial-roofing/, /projects/ | 0 | Serves the GC/builder channel.
P005 | 1 | Planned | Static | /for-restoration/ | restoration roofing subcontractor austin |  | Commercial | Roofing Partner for Restoration Companies ¦ Portillo Roofing | 60 | Storm Overflow Roofing for Restoration Companies |  |  | Overflow capacity; response time after a storm; estimate format (Xactimate only if true); photo documentation standard; willingness to work under their brand; insurance on file. | Service + BreadcrumbList | - | Y | index | /services/hail-damage-roof-repair/, /projects/ | 0 | NEW (council). Serves restoration/insurance overflow channel. Ship before March.
P006 | 1 | Live | Hub | /services/ | roofing services austin |  | Navigational | Roofing Services in Austin, TX ¦ Portillo Roofing | 49 | Roofing Services |  |  | 1-paragraph intro naming what's in the section; card per child page with photo; no thin filler. | CollectionPage + BreadcrumbList | - | Y | index | Every roofing service page | 0 | Live as services.html -> 301 to /services/. Becomes roofing-only hub (remodeling/countertops move out).
P007 | 1 | Draft | Hub | /projects/ | roofing projects austin |  | Navigational | Roofing Projects & Portfolio ¦ Portillo Roofing | 47 | Our Work |  |  | 1-paragraph intro naming what's in the section; card per child page with photo; no thin filler. | CollectionPage + BreadcrumbList | - | Y | index | Every project page | 0 | portfolio.html on relaunch branch; must render project pages as static HTML.
P008 | 1 | Planned | Roofing service | /services/roof-replacement/ | roof replacement austin | reroof austin; roof replacement company austin; new roof austin | Transactional | Roof Replacement in Austin, TX ¦ Portillo Roofing | 49 | Roof Replacement in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: TXST Apartments (400 sq reroof) | Y | index | Live city pages; Projects: TXST Apartments; Guides: roof-replacement-cost-austin, how-long-does-a-roof-last-in-texas, roofing-permit-austin, how-to-choose-a-roofer-austin, roof-replacement-timeline | 0 | Cost intent belongs to the cost guide - link to it, don't target it here.
P009 | 1 | Planned | Roofing service | /services/roof-repair/ | roof repair austin | roof leak repair austin; roof repair company austin | Transactional | Roof Repair in Austin, TX ¦ Portillo Roofing | 44 | Roof Repair in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Listed on current site - need repair job photos | ? | index | Live city pages | 0 | Owns '<service> austin'; no /areas/austin/ page. Cross-link to ceiling/drywall repair section after leaks.
P010 | 1 | Planned | Roofing service | /services/metal-roofing/ | metal roofing austin | standing seam metal roof austin; metal roof contractor austin; custom metal fascia; curved standing seam panels | Transactional | Metal Roofing in Austin, TX ¦ Portillo Roofing | 46 | Standing Seam Metal Roofing in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Inwood, Shoalwood, Knollwood, Curved Ridges, Yuapon | Y | index | Live city pages; Projects: Inwood, Curved Ridges, Yuapon; Guides: metal-roof-cost-austin, metal-vs-shingle-roof-texas, standing-seam-vs-exposed-fastener | 0 | Signature niche. Custom fabrication lives here as a section (see #custom-fabrication row).
P011 | 1 | Planned | Roofing service | /services/flat-roofing/ | tpo roofing austin | flat roof repair austin; flat roof replacement austin | Transactional | Flat & TPO Roofing in Austin, TX ¦ Portillo Roofing | 51 | Flat & TPO Roofing in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Mendez School (TPO), Knollwood | Y | index | Live city pages; Projects: Mendez School; Guides: tpo-vs-modified-bitumen | 0 | Check Planner: if 'flat roof repair austin' outranks 'tpo roofing austin', swap primary.
P012 | 1 | Planned | Roofing service | /services/commercial-roofing/ | commercial roofing austin | commercial roofing contractor austin; commercial roof replacement austin; commercial tpo contractor | Transactional | Commercial Roofing in Austin, TX ¦ Portillo Roofing | 51 | Commercial Roofing in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Travis County Jail, Mendez School, TXST, UT Batter's Eye | Y | index | Live city pages; Projects: Travis County Jail, UT Austin Batter's Eye | 0 | Council split: economics seat would merge with Flat/TPO. Kept separate (different buyer).
P013 | 1 | Planned | Roofing service | /services/new-construction-roofing/ | new construction roofing austin | builder roofing contractor austin; new home roofing austin | Transactional | New Construction Roofing in Austin, TX ¦ Portillo Roofing | 57 | New Construction Roofing in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Inwood, Shoalwood, Knollwood, Fiset | Y | index | Live city pages; Projects: Knollwood, Shoalwood, Fiset | 0 | 'roofing subcontractor austin' is owned by /for-builders/.
P014 | 1 | Planned | Roofing service | /services/hail-damage-roof-repair/ | hail damage roof repair austin | storm damage roof repair austin; hail damage roof inspection; wind damage roof repair; insurance roof inspection austin | Transactional | Hail & Storm Damage Repair in Austin, TX ¦ Portillo Roofing | 59 | Hail & Storm Damage Repair in Austin & Central Texas |  |  | COMPLIANCE (Ins. Code 4102.163; Bus. & Com. Code 27.02): OK to say inspect, photograph, write a repair scope, meet the adjuster on site as the contractor. NEVER say negotiate, represent you, fair coverage, maximize your claim, direct insurance billing, or anything about covering/waiving the deductible. Include a plain statement that the homeowner pays their deductible. 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Listed on current site - need storm job photos | ? | index | Live city pages; Guides: does-insurance-cover-hail-damage-texas, signs-of-hail-damage-on-roof | 0 | Merged with old 'Roof Insurance Claim Help' page. COMPLIANCE: see Copy column. Ship before March (hail season).
P015 | 1 | Section | Section | /services/metal-roofing/#custom-fabrication | custom metal fascia austin | curved standing seam roof; tapered metal fascia | Transactional | (section - uses parent page title) |  | H2: Custom Metal Fascia & Curved Panels |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Yuapon, Curved Ridges | Y | index | Parent: /services/metal-roofing/ | 0 | Category: Roofing.
P016 | 1 | Planned | City | /areas/dale/ | roofer dale | roofing company dale; roofing contractor dale tx; roof repair dale | Transactional | Dale, TX Roofing Contractor ¦ Portillo Roofing | 46 | Roofing Contractor in Dale, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | ? | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: South core (All services incl. add-ons). Home base - build first; still needs local job photos.
P017 | 1 | Planned | City | /areas/san-marcos/ | roofer san marcos | roofing company san marcos; roofing contractor san marcos tx; roof repair san marcos | Transactional | San Marcos, TX Roofing Contractor ¦ Portillo Roofing | 52 | Roofing Contractor in San Marcos, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | Y | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: South core (All services incl. add-ons). TXST Apartments 400-sq reroof (owner confirmed San Marcos).
P018 | 1 | Draft | Project | /projects/travis-county-jail/ | curved metal roof & steel frame project |  | Proof | Travis County Jail ¦ Portillo Roofing | 37 | Travis County Jail: Curved Metal Roof & Steel Frame |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/commercial-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P019 | 1 | Draft | Project | /projects/ut-austin-batters-eye/ | removable metal panel system project |  | Proof | UT Austin Batter's Eye ¦ Portillo Roofing | 41 | UT Austin Batter's Eye: Removable Metal Panel System |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/commercial-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P020 | 1 | Draft | Project | /projects/inwood/ | standing seam metal roof project |  | Proof | Inwood ¦ Portillo Roofing | 25 | Inwood: Standing Seam Metal Roof |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/metal-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P021 | 1 | Draft | Project | /projects/txst-apartments/ | 400-square shingle reroof project |  | Proof | TXST Apartments ¦ Portillo Roofing | 34 | TXST Apartments: 400-Square Shingle Reroof |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/roof-replacement/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P022 | 1 | Draft | Project | /projects/mendez-school/ | commercial tpo roof project |  | Proof | Mendez School ¦ Portillo Roofing | 32 | Mendez School: Commercial TPO Roof |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/flat-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P023 | 1 | Planned | Guide | /guides/roof-replacement-cost-austin/ | roof replacement cost austin | new roof cost austin; cost per square roofing austin | Informational | How Much Does a Roof Replacement Cost in Austin? | 48 | How Much Does a Roof Replacement Cost in Austin? |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/roof-replacement/ | 0
P024 | 1 | Live | Utility | /thank-you/ | - |  | - | Thank You ¦ Portillo Roofing | 28 | Thank You |  |  |  | - | - | Y | noindex | - | 0 | Currently indexable - set noindex.
P025 | 1 | Live | Utility | /privacy-policy/ | - |  | - | Privacy Policy ¦ Portillo Roofing | 33 | Privacy Policy |  |  |  | - | - | Y | index | - | 0
P026 | 1 | Live | Utility | /terms-of-service/ | - |  | - | Terms of Service ¦ Portillo Roofing | 35 | Terms of Service |  |  |  | - | - | Y | index | - | 0
P027 | 2 | Planned | Static | /reviews/ | portillo roofing reviews |  | Navigational | Customer Reviews ¦ Portillo Roofing | 35 | What Our Customers Say |  |  | Only real reviews with first name + town, linked to Google/BBB source. FTC 16 CFR 465 bans fake/AI testimonials. | WebPage (no self-serving AggregateRating) | - | Y | index | /projects/, /contact/ | 0 | Wait until 5+ real reviews.
P028 | 2 | Planned | Hub | /remodeling/ | remodeling contractor austin |  | Navigational | Remodeling & Home Services in Austin ¦ Portillo Roofing | 55 | Remodeling, Painting & Exterior Services |  |  | 1-paragraph intro naming what's in the section; card per child page with photo; no thin filler. | CollectionPage + BreadcrumbList | - | Y | index | Remodeling pages + every section | 0 | One hub holds remodeling, painting, coatings, tile, drywall and pressure washing as sections (council: no separate hubs).
P029 | 2 | Planned | Hub | /countertops/ | custom countertops austin |  | Navigational | Custom Countertops in Austin, TX ¦ Portillo Roofing | 51 | Granite, Epoxy & River Countertops |  |  | 1-paragraph intro naming what's in the section; card per child page with photo; no thin filler. | CollectionPage + BreadcrumbList | - | Y | index | Countertop sections | 0 | Specialty line as ONE page with sections; split a section out only when it earns it.
P030 | 2 | Planned | Hub | /areas/ | roofing service area central texas |  | Navigational | Service Areas - Central Texas ¦ Portillo Roofing | 48 | Where We Work |  |  | 1-paragraph intro naming what's in the section; card per child page with photo; no thin filler. | CollectionPage + BreadcrumbList | - | Y | index | Every live city page | 0 | Lists all 14 towns with zones; links only to city pages that are live.
P031 | 2 | Planned | Hub | /guides/ | roofing guides texas |  | Navigational | Roofing Guides & Answers ¦ Portillo Roofing | 43 | Roofing Questions, Answered |  |  | 1-paragraph intro naming what's in the section; card per child page with photo; no thin filler. | CollectionPage + BreadcrumbList | - | Y | index | Every guide | 0
P032 | 2 | Planned | Roofing service | /services/shingle-roofing/ | shingle roofing austin | asphalt shingle roof austin; architectural shingles austin; impact resistant shingles austin | Transactional | Shingle Roofing in Austin, TX ¦ Portillo Roofing | 48 | Shingle Roofing in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: TXST Apartments | Y | index | Live city pages | 0
P033 | 2 | Planned | Roofing service | /services/tile-roof-repair/ | tile roof repair austin | clay tile roof repair austin; concrete tile roof repair | Transactional | Tile Roof Repair in Austin, TX ¦ Portillo Roofing | 49 | Tile Roof Repair in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Tile repair workflow (torch-down underlayment) - need photos | ? | index | Live city pages; Guides: tile-roof-repair-vs-replacement | 0 | Underlayment-cost question is owned by the tile guide.
P034 | 2 | Planned | Roofing service | /services/roof-inspection/ | roof inspection austin | free roof inspection austin; roof inspection for home sale | Transactional | Roof Inspection in Austin, TX ¦ Portillo Roofing | 48 | Roof Inspection in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Listed on current site | ? | index | Live city pages | 0
P035 | 2 | Planned | Roofing service | /services/roof-coating/ | roof coating austin | silicone roof coating austin; elastomeric roof coating; flat roof coating austin | Transactional | Roof Coating in Austin, TX ¦ Portillo Roofing | 45 | Silicone & Elastomeric Roof Coating in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Owner listed 'coating' - CONFIRM roof coatings specifically | ? | index | Live city pages | 0 | Offered? CONFIRM.
P036 | 2 | Gated | Trade service | /remodeling/home-renovation/ | home renovation austin | whole house remodel austin; interior renovation contractor austin | Transactional | Whole-Home Interior Renovation in Austin, TX | 44 | Whole-Home Interior Renovation in Austin |  |  | Direct answer up top; price range from your jobs; 4+ before/after photos; scope steps; how it pairs with roofing/remodel; FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList | Finished job + before/after photos. Evidence: Villa Park (in progress), Dodd (quoted) - not proof until complete | N | index | /remodeling/; related projects | 0 | Category: Remodeling.
P037 | 2 | Gated | Trade service | /remodeling/patio-covers/ | patio cover builder austin | covered patio addition austin; patio roof austin | Transactional | Patio Covers in Austin, TX ¦ Portillo Roofing | 45 | Patio Covers & Additions in Austin |  |  | Direct answer up top; price range from your jobs; 4+ before/after photos; scope steps; how it pairs with roofing/remodel; FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList | Finished job + before/after photos. Evidence: Huntridge (quoted) - not proof until complete | N | index | /remodeling/; related projects | 0 | Category: Remodeling.
P038 | 2 | Gated | Trade service | /remodeling/epoxy-flooring/ | epoxy flooring austin | garage floor coating austin; epoxy garage floor austin; polyaspartic floor coating | Transactional | Epoxy Floor in Austin, TX ¦ Portillo Roofing | 44 | Epoxy Floor & Garage Coatings in Austin |  |  | Direct answer up top; price range from your jobs; 4+ before/after photos; scope steps; how it pairs with roofing/remodel; FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList | Finished job + before/after photos. Evidence: On relaunch branch - need finished-floor photos | ? | index | /remodeling/; related projects | 0 | Category: Remodeling.
P039 | 2 | Section | Section | /remodeling/#kitchen | kitchen remodel austin | kitchen remodeling contractor austin | Transactional | (section - uses parent page title) |  | H2: Kitchen Remodeling |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Dissected from whole-home work | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P040 | 2 | Section | Section | /remodeling/#bathroom | bathroom remodel austin | shower remodel austin | Transactional | (section - uses parent page title) |  | H2: Bathroom Remodeling |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Dissected from whole-home work | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P041 | 2 | Section | Section | /remodeling/#drywall-ceiling | drywall repair austin | ceiling repair austin; water damage drywall repair austin | Transactional | (section - uses parent page title) |  | H2: Drywall & Ceiling Repair |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Ceiling repair scopes; pairs with leak repairs | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P042 | 2 | Section | Section | /remodeling/#tile | tile installation austin | bathroom tile installer austin; backsplash installation austin | Transactional | (section - uses parent page title) |  | H2: Tile Installation |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Pool waterline tile; quote system covers tile | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P043 | 2 | Section | Section | /remodeling/#interior-painting | interior painting austin | interior painters austin | Transactional | (section - uses parent page title) |  | H2: Interior Painting |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Owner confirmed painting | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P044 | 2 | Section | Section | /remodeling/#exterior-painting | exterior painting austin | exterior house painters austin; house painters austin | Transactional | (section - uses parent page title) |  | H2: Exterior Painting |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Owner confirmed painting | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P045 | 2 | Section | Section | /remodeling/#pressure-washing | house washing austin | soft wash house austin | Transactional | (section - uses parent page title) |  | H2: House Soft Washing |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Owner confirmed power washing - low ticket, add-on | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P046 | 2 | Section | Section | /remodeling/#concrete-cleaning | driveway cleaning austin | concrete cleaning austin; patio pressure washing austin | Transactional | (section - uses parent page title) |  | H2: Driveway & Concrete Cleaning |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Owner confirmed power washing - low ticket, add-on | ? | index | Parent: /remodeling/ | 0 | Category: Remodeling.
P047 | 2 | Section | Section | /countertops/#granite | granite countertops austin | granite countertop installation austin | Transactional | (section - uses parent page title) |  | H2: Granite Countertops |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: On relaunch branch | ? | index | Parent: /countertops/ | 0 | Category: Countertops.
P048 | 2 | Section | Section | /countertops/#epoxy-river | epoxy countertops austin | river table countertop; live edge epoxy countertop austin | Transactional | (section - uses parent page title) |  | H2: Epoxy & River Countertops |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: On relaunch branch + photos | Y | index | Parent: /countertops/ | 0 | Category: Countertops.
P049 | 2 | Gated | City | /areas/lockhart/ | roofer lockhart | roofing company lockhart; roofing contractor lockhart tx; roof repair lockhart | Transactional | Lockhart, TX Roofing Contractor ¦ Portillo Roofing | 50 | Roofing Contractor in Lockhart, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: South core (All services incl. add-ons).
P050 | 2 | Gated | City | /areas/bastrop/ | roofer bastrop | roofing company bastrop; roofing contractor bastrop tx; roof repair bastrop | Transactional | Bastrop, TX Roofing Contractor ¦ Portillo Roofing | 49 | Roofing Contractor in Bastrop, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: South core (All services incl. add-ons). Dodd job is quoted, not complete - not proof yet.
P051 | 2 | Gated | City | /areas/kyle/ | roofer kyle | roofing company kyle; roofing contractor kyle tx; roof repair kyle | Transactional | Kyle, TX Roofing Contractor ¦ Portillo Roofing | 46 | Roofing Contractor in Kyle, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: South core (All services incl. add-ons).
P052 | 2 | Gated | City | /areas/buda/ | roofer buda | roofing company buda; roofing contractor buda tx; roof repair buda | Transactional | Buda, TX Roofing Contractor ¦ Portillo Roofing | 46 | Roofing Contractor in Buda, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: South core (All services incl. add-ons).
P053 | 2 | Draft | Project | /projects/curved-ridges/ | curved standing seam panels project |  | Proof | Curved Ridges ¦ Portillo Roofing | 32 | Curved Ridges: Curved Standing Seam Panels |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/metal-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P054 | 2 | Draft | Project | /projects/yuapon/ | tapered metal fascia project |  | Proof | Yuapon ¦ Portillo Roofing | 25 | Yuapon: Tapered Metal Fascia |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/metal-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P055 | 2 | Draft | Project | /projects/knollwood/ | metal & tpo new build project |  | Proof | Knollwood ¦ Portillo Roofing | 28 | Knollwood: Metal & TPO New Build |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/new-construction-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P056 | 2 | Draft | Project | /projects/shoalwood/ | snaplok standing seam project |  | Proof | Shoalwood ¦ Portillo Roofing | 28 | Shoalwood: SnapLok Standing Seam |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | Y | index | /services/new-construction-roofing/; town page for job location | 0 | Need job town. GC jobs: get builder OK before publishing.
P057 | 2 | Planned | Guide | /guides/metal-roof-cost-austin/ | metal roof cost austin | standing seam metal roof cost per square foot texas | Informational | Standing Seam Metal Roof Cost in Austin | 39 | Standing Seam Metal Roof Cost in Austin |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/metal-roofing/ | 0
P058 | 2 | Planned | Guide | /guides/metal-vs-shingle-roof-texas/ | metal vs shingle roof texas | is a metal roof worth it in texas; best roof for texas heat | Informational | Metal vs. Shingle Roofs in Central Texas Heat | 45 | Metal vs. Shingle Roofs in Central Texas Heat |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/metal-roofing/ | 0
P059 | 2 | Planned | Guide | /guides/does-insurance-cover-hail-damage-texas/ | does insurance cover hail damage roof texas | hail damage roof claim process texas | Informational | Does Homeowners Insurance Cover Hail Damage in Texas? | 53 | Does Homeowners Insurance Cover Hail Damage in Texas? |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. Informational only - no offer to handle or negotiate claims. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/hail-damage-roof-repair/ | 0
P060 | 2 | Planned | Guide | /guides/signs-of-hail-damage-on-roof/ | signs of hail damage on roof | what does hail damage look like on shingles; hail damage metal roof | Informational | Signs of Hail Damage on Your Roof (With Photos) | 47 | Signs of Hail Damage on Your Roof (With Photos) |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/hail-damage-roof-repair/ | 0
P061 | 2 | Planned | Guide | /guides/how-long-does-a-roof-last-in-texas/ | how long does a roof last in texas | shingle roof lifespan texas; metal roof lifespan | Informational | How Long Does a Roof Last in Texas? | 35 | How Long Does a Roof Last in Texas? |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/roof-replacement/ | 0
P062 | 2 | Planned | Service x City | /areas/san-marcos/roof-replacement/ | roof replacement san marcos | roof replacement san marcos tx | Transactional | Roof Replacement in San Marcos, TX ¦ Portillo Roofing | 53 | Roof Replacement in San Marcos, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | Y | index | /areas/san-marcos/, /services/roof-replacement/, matching project | 0 | Un-gated: TXST Apartments reroof is in San Marcos.
P063 | 3 | Planned | Roofing service | /services/gutters/ | gutter installation austin | seamless gutters austin; gutter replacement austin | Transactional | Gutter Installation in Austin, TX ¦ Portillo Roofing | 52 | Gutters in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Travis County Jail scope included gutters - CONFIRM standalone | ? | index | Live city pages | 0 | Offered? CONFIRM.
P064 | 3 | Gated | Roofing service | /services/emergency-roof-repair/ | emergency roof repair austin | roof tarp service austin; 24 hour roofer austin | Transactional | Emergency Roof Repair in Austin, TX ¦ Portillo Roofing | 54 | Emergency Roof Repair in Austin & Central Texas |  |  | 40-60 word direct answer up top; dated $/square range from YOUR jobs + what moves it; specs (panel profile, gauge, underlayment, impact rating); typical duration; permit office; 2+ captioned project photos; 5-8 FAQs unique to this page; last-updated date. | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result) | Photos of this service + process + FAQs. Evidence: Site claims 24/7 hotline - no process confirmed | N | index | Live city pages | 0 | Offered? CONFIRM. Gate: only with a real after-hours phone process.
P065 | 3 | Section | Section | /remodeling/#flooring | flooring installation austin | vinyl plank flooring installation austin | Transactional | (section - uses parent page title) |  | H2: Flooring Installation |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: CONFIRM offered standalone | ? | index | Parent: /remodeling/ | 0 | Offered? CONFIRM. Category: Remodeling.
P066 | 3 | Section | Section | /remodeling/#pool-tile | pool tile replacement austin | pool coping replacement austin | Transactional | (section - uses parent page title) |  | H2: Pool Tile & Coping |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: Pool renovation job - CONFIRM complete | ? | index | Parent: /remodeling/ | 0 | Offered? CONFIRM. Category: Remodeling.
P067 | 3 | Section | Section | /remodeling/#cabinets | cabinet painting austin | kitchen cabinet refinishing austin | Transactional | (section - uses parent page title) |  | H2: Cabinet Painting & Refinishing |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: CONFIRM offered | ? | index | Parent: /remodeling/ | 0 | Offered? CONFIRM. Category: Remodeling.
P068 | 3 | Section | Section | /remodeling/#staining | fence staining austin | deck staining austin | Transactional | (section - uses parent page title) |  | H2: Deck & Fence Staining |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: CONFIRM offered - low ticket, add-on only | ? | index | Parent: /remodeling/ | 0 | Offered? CONFIRM. Category: Remodeling.
P069 | 3 | Section | Section | /services/roof-inspection/#roof-cleaning | roof cleaning austin | roof soft wash austin | Transactional | (section - uses parent page title) |  | H2: Roof Soft Washing |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: CONFIRM offered | ? | index | Parent: /services/roof-inspection/ | 0 | Offered? CONFIRM. Category: Roofing.
P070 | 3 | Section | Section | /countertops/#quartz | quartz countertops austin | quartz countertop installation austin | Transactional | (section - uses parent page title) |  | H2: Quartz Countertops |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: CONFIRM offered | ? | index | Parent: /countertops/ | 0 | Offered? CONFIRM. Category: Countertops.
P071 | 3 | Section | Section | /countertops/#resurfacing | countertop resurfacing austin | epoxy countertop over laminate | Transactional | (section - uses parent page title) |  | H2: Countertop Resurfacing |  |  | Inside the parent page: H2 named for the service, 80-150 words, 2+ photos, price range or 'typical scope', link to contact. Promote to its own page when proof + volume justify it. | None of its own - listed in parent page's Service / hasOfferCatalog | Photos of this work. Evidence: CONFIRM offered | ? | index | Parent: /countertops/ | 0 | Offered? CONFIRM. Category: Countertops.
P072 | 3 | Gated | City | /areas/manor/ | roofer manor | roofing company manor; roofing contractor manor tx; roof repair manor | Transactional | Manor, TX Roofing Contractor ¦ Portillo Roofing | 47 | Roofing Contractor in Manor, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: East / metro (Roofing + remodeling; no low-ticket add-ons).
P073 | 3 | Gated | City | /areas/pflugerville/ | roofer pflugerville | roofing company pflugerville; roofing contractor pflugerville tx; roof repair pflugerville | Transactional | Pflugerville, TX Roofing Contractor ¦ Portillo Roofing | 54 | Roofing Contractor in Pflugerville, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: East / metro (Roofing + remodeling; no low-ticket add-ons). Currently listed on site.
P074 | 3 | Gated | City | /areas/round-rock/ | roofer round rock | roofing company round rock; roofing contractor round rock tx; roof repair round rock | Transactional | Round Rock, TX Roofing Contractor ¦ Portillo Roofing | 52 | Roofing Contractor in Round Rock, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: North (Roofing replacement, metal, commercial, new construction only). Currently listed on site.
P075 | 3 | Gated | City | /areas/hutto/ | roofer hutto | roofing company hutto; roofing contractor hutto tx; roof repair hutto | Transactional | Hutto, TX Roofing Contractor ¦ Portillo Roofing | 47 | Roofing Contractor in Hutto, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: North (Roofing replacement, metal, commercial, new construction only).
P076 | 3 | Gated | City | /areas/cedar-park/ | roofer cedar park | roofing company cedar park; roofing contractor cedar park tx; roof repair cedar park | Transactional | Cedar Park, TX Roofing Contractor ¦ Portillo Roofing | 52 | Roofing Contractor in Cedar Park, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: North (Roofing replacement, metal, commercial, new construction only). Currently listed on site.
P077 | 3 | Gated | City | /areas/leander/ | roofer leander | roofing company leander; roofing contractor leander tx; roof repair leander | Transactional | Leander, TX Roofing Contractor ¦ Portillo Roofing | 49 | Roofing Contractor in Leander, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: North (Roofing replacement, metal, commercial, new construction only). Currently listed on site.
P078 | 3 | Gated | City | /areas/georgetown/ | roofer georgetown | roofing company georgetown; roofing contractor georgetown tx; roof repair georgetown | Transactional | Georgetown, TX Roofing Contractor ¦ Portillo Roofing | 52 | Roofing Contractor in Georgetown, TX |  |  | Number of jobs completed in this town; 1+ project with photos; permit authority; housing stock / HOA notes; dated local hail events; what we take on in this zone; links to nearby towns. Never a find-and-replace of another town page. | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town. | >=1 completed job in town with photos (2+ preferred) | N | index | Roofing services; live Service x City pages for this town; projects here; 2 nearest towns | 0 | Zone: North (Roofing replacement, metal, commercial, new construction only). Currently listed on site.
P079 | 3 | Gated | Project | /projects/fiset/ | new construction roof project |  | Proof | Fiset ¦ Portillo Roofing | 24 | Fiset: New Construction Roof |  |  | City, year, squares, system/materials, client type (GC / owner / public), duration, problem -> fix, 6+ captioned photos, written photo consent. Must be static HTML (not loaded from portfolio-data.js). | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList | Photos + scope write-up (exists in portfolio-data.js) + photo consent | N | index | /services/new-construction-roofing/; town page for job location | 0 | In progress - publish when complete. Need job town. GC jobs: get builder OK before publishing.
P080 | 3 | Planned | Guide | /guides/standing-seam-vs-exposed-fastener/ | standing seam vs exposed fastener metal roof | snap lock vs mechanical lock standing seam | Informational | Standing Seam vs. Exposed-Fastener Metal Roofs | 46 | Standing Seam vs. Exposed-Fastener Metal Roofs |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/metal-roofing/ | 0
P081 | 3 | Planned | Guide | /guides/tile-roof-repair-vs-replacement/ | tile roof underlayment replacement cost | tile roof underlayment replacement; reuse roof tiles | Informational | Tile Roof: Repair the Underlayment or Replace? | 46 | Tile Roof: Repair the Underlayment or Replace? |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/tile-roof-repair/ | 0
P082 | 3 | Planned | Guide | /guides/tpo-vs-modified-bitumen/ | tpo vs modified bitumen | best flat roof material texas | Informational | TPO vs. Modified Bitumen for Flat Roofs | 39 | TPO vs. Modified Bitumen for Flat Roofs |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/flat-roofing/ | 0
P083 | 3 | Planned | Guide | /guides/roofing-permit-austin/ | roofing permit austin | city of austin reroof permit | Informational | Do You Need a Permit to Replace a Roof in Austin? | 49 | Do You Need a Permit to Replace a Roof in Austin? |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/roof-replacement/ | 0
P084 | 3 | Planned | Guide | /guides/how-to-choose-a-roofer-austin/ | how to choose a roofer austin | roofing scams after hail storm texas | Informational | How to Choose a Roofing Contractor in Austin | 44 | How to Choose a Roofing Contractor in Austin |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/roof-replacement/ | 0
P085 | 3 | Planned | Guide | /guides/roof-replacement-timeline/ | how long does a roof replacement take | roof replacement process | Informational | What Happens on Roof Replacement Day | 36 | What Happens on Roof Replacement Day |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /services/roof-replacement/ | 0
P086 | 3 | Planned | Guide | /guides/granite-vs-epoxy-countertops/ | granite vs epoxy countertops | epoxy countertop durability | Informational | Granite vs. Epoxy Countertops | 29 | Granite vs. Epoxy Countertops |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /countertops/ | 0
P087 | 3 | Planned | Guide | /guides/home-renovation-cost-austin/ | home renovation cost austin | cost to gut and remodel a house austin | Informational | Whole-Home Renovation Cost in Austin | 36 | Whole-Home Renovation Cost in Austin |  |  | Byline (Marco Portillo + credentials); direct answer first; your own numbers; cited sources; last-updated date. | Article (author Person w/ sameAs, dateModified) + BreadcrumbList | Your own numbers / photos; byline | ? | index | /remodeling/ | 0
P088 | 3 | Gated | Service x City | /areas/dale/roof-replacement/ | roof replacement dale | roof replacement dale tx | Transactional | Roof Replacement in Dale, TX ¦ Portillo Roofing | 47 | Roof Replacement in Dale, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/dale/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P089 | 3 | Gated | Service x City | /areas/dale/metal-roofing/ | metal roofing dale | metal roofing dale tx | Transactional | Metal Roofing in Dale, TX ¦ Portillo Roofing | 44 | Standing Seam Metal Roofing in Dale, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/dale/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P090 | 3 | Gated | Service x City | /areas/dale/hail-damage-roof-repair/ | hail damage roof repair dale | hail damage roof repair dale tx | Transactional | Hail & Storm Damage Repair in Dale, TX ¦ Portillo Roofing | 57 | Hail & Storm Damage Repair in Dale, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/dale/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P091 | 3 | Gated | Service x City | /areas/san-marcos/metal-roofing/ | metal roofing san marcos | metal roofing san marcos tx | Transactional | Metal Roofing in San Marcos, TX ¦ Portillo Roofing | 50 | Standing Seam Metal Roofing in San Marcos, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/san-marcos/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P092 | 3 | Gated | Service x City | /areas/san-marcos/hail-damage-roof-repair/ | hail damage roof repair san marcos | hail damage roof repair san marcos tx | Transactional | Hail & Storm Damage Repair in San Marcos, TX | 44 | Hail & Storm Damage Repair in San Marcos, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/san-marcos/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P093 | 3 | Gated | Service x City | /areas/lockhart/roof-replacement/ | roof replacement lockhart | roof replacement lockhart tx | Transactional | Roof Replacement in Lockhart, TX ¦ Portillo Roofing | 51 | Roof Replacement in Lockhart, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/lockhart/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P094 | 3 | Gated | Service x City | /areas/lockhart/metal-roofing/ | metal roofing lockhart | metal roofing lockhart tx | Transactional | Metal Roofing in Lockhart, TX ¦ Portillo Roofing | 48 | Standing Seam Metal Roofing in Lockhart, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/lockhart/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P095 | 3 | Gated | Service x City | /areas/lockhart/hail-damage-roof-repair/ | hail damage roof repair lockhart | hail damage roof repair lockhart tx | Transactional | Hail & Storm Damage Repair in Lockhart, TX | 42 | Hail & Storm Damage Repair in Lockhart, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/lockhart/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P096 | 3 | Gated | Service x City | /areas/bastrop/roof-replacement/ | roof replacement bastrop | roof replacement bastrop tx | Transactional | Roof Replacement in Bastrop, TX ¦ Portillo Roofing | 50 | Roof Replacement in Bastrop, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/bastrop/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P097 | 3 | Gated | Service x City | /areas/bastrop/metal-roofing/ | metal roofing bastrop | metal roofing bastrop tx | Transactional | Metal Roofing in Bastrop, TX ¦ Portillo Roofing | 47 | Standing Seam Metal Roofing in Bastrop, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/bastrop/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P098 | 3 | Gated | Service x City | /areas/bastrop/hail-damage-roof-repair/ | hail damage roof repair bastrop | hail damage roof repair bastrop tx | Transactional | Hail & Storm Damage Repair in Bastrop, TX ¦ Portillo Roofing | 60 | Hail & Storm Damage Repair in Bastrop, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/bastrop/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P099 | 3 | Gated | Service x City | /areas/kyle/roof-replacement/ | roof replacement kyle | roof replacement kyle tx | Transactional | Roof Replacement in Kyle, TX ¦ Portillo Roofing | 47 | Roof Replacement in Kyle, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/kyle/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P100 | 3 | Gated | Service x City | /areas/kyle/metal-roofing/ | metal roofing kyle | metal roofing kyle tx | Transactional | Metal Roofing in Kyle, TX ¦ Portillo Roofing | 44 | Standing Seam Metal Roofing in Kyle, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/kyle/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P101 | 3 | Gated | Service x City | /areas/kyle/hail-damage-roof-repair/ | hail damage roof repair kyle | hail damage roof repair kyle tx | Transactional | Hail & Storm Damage Repair in Kyle, TX ¦ Portillo Roofing | 57 | Hail & Storm Damage Repair in Kyle, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/kyle/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P102 | 3 | Gated | Service x City | /areas/buda/roof-replacement/ | roof replacement buda | roof replacement buda tx | Transactional | Roof Replacement in Buda, TX ¦ Portillo Roofing | 47 | Roof Replacement in Buda, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/buda/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P103 | 3 | Gated | Service x City | /areas/buda/metal-roofing/ | metal roofing buda | metal roofing buda tx | Transactional | Metal Roofing in Buda, TX ¦ Portillo Roofing | 44 | Standing Seam Metal Roofing in Buda, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/buda/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P104 | 3 | Gated | Service x City | /areas/buda/hail-damage-roof-repair/ | hail damage roof repair buda | hail damage roof repair buda tx | Transactional | Hail & Storm Damage Repair in Buda, TX ¦ Portillo Roofing | 57 | Hail & Storm Damage Repair in Buda, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/buda/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P105 | 3 | Gated | Service x City | /areas/manor/roof-replacement/ | roof replacement manor | roof replacement manor tx | Transactional | Roof Replacement in Manor, TX ¦ Portillo Roofing | 48 | Roof Replacement in Manor, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/manor/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P106 | 3 | Gated | Service x City | /areas/manor/metal-roofing/ | metal roofing manor | metal roofing manor tx | Transactional | Metal Roofing in Manor, TX ¦ Portillo Roofing | 45 | Standing Seam Metal Roofing in Manor, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/manor/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P107 | 3 | Gated | Service x City | /areas/manor/hail-damage-roof-repair/ | hail damage roof repair manor | hail damage roof repair manor tx | Transactional | Hail & Storm Damage Repair in Manor, TX ¦ Portillo Roofing | 58 | Hail & Storm Damage Repair in Manor, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/manor/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P108 | 3 | Gated | Service x City | /areas/pflugerville/roof-replacement/ | roof replacement pflugerville | roof replacement pflugerville tx | Transactional | Roof Replacement in Pflugerville, TX ¦ Portillo Roofing | 55 | Roof Replacement in Pflugerville, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/pflugerville/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P109 | 3 | Gated | Service x City | /areas/pflugerville/metal-roofing/ | metal roofing pflugerville | metal roofing pflugerville tx | Transactional | Metal Roofing in Pflugerville, TX ¦ Portillo Roofing | 52 | Standing Seam Metal Roofing in Pflugerville, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/pflugerville/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P110 | 3 | Gated | Service x City | /areas/pflugerville/hail-damage-roof-repair/ | hail damage roof repair pflugerville | hail damage roof repair pflugerville tx | Transactional | Hail & Storm Damage Repair in Pflugerville, TX | 46 | Hail & Storm Damage Repair in Pflugerville, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/pflugerville/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P111 | 3 | Gated | Service x City | /areas/round-rock/roof-replacement/ | roof replacement round rock | roof replacement round rock tx | Transactional | Roof Replacement in Round Rock, TX ¦ Portillo Roofing | 53 | Roof Replacement in Round Rock, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/round-rock/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P112 | 3 | Gated | Service x City | /areas/round-rock/metal-roofing/ | metal roofing round rock | metal roofing round rock tx | Transactional | Metal Roofing in Round Rock, TX ¦ Portillo Roofing | 50 | Standing Seam Metal Roofing in Round Rock, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/round-rock/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P113 | 3 | Gated | Service x City | /areas/round-rock/hail-damage-roof-repair/ | hail damage roof repair round rock | hail damage roof repair round rock tx | Transactional | Hail & Storm Damage Repair in Round Rock, TX | 44 | Hail & Storm Damage Repair in Round Rock, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/round-rock/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P114 | 3 | Gated | Service x City | /areas/hutto/roof-replacement/ | roof replacement hutto | roof replacement hutto tx | Transactional | Roof Replacement in Hutto, TX ¦ Portillo Roofing | 48 | Roof Replacement in Hutto, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/hutto/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P115 | 3 | Gated | Service x City | /areas/hutto/metal-roofing/ | metal roofing hutto | metal roofing hutto tx | Transactional | Metal Roofing in Hutto, TX ¦ Portillo Roofing | 45 | Standing Seam Metal Roofing in Hutto, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/hutto/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P116 | 3 | Gated | Service x City | /areas/hutto/hail-damage-roof-repair/ | hail damage roof repair hutto | hail damage roof repair hutto tx | Transactional | Hail & Storm Damage Repair in Hutto, TX ¦ Portillo Roofing | 58 | Hail & Storm Damage Repair in Hutto, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/hutto/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P117 | 3 | Gated | Service x City | /areas/cedar-park/roof-replacement/ | roof replacement cedar park | roof replacement cedar park tx | Transactional | Roof Replacement in Cedar Park, TX ¦ Portillo Roofing | 53 | Roof Replacement in Cedar Park, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/cedar-park/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P118 | 3 | Gated | Service x City | /areas/cedar-park/metal-roofing/ | metal roofing cedar park | metal roofing cedar park tx | Transactional | Metal Roofing in Cedar Park, TX ¦ Portillo Roofing | 50 | Standing Seam Metal Roofing in Cedar Park, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/cedar-park/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P119 | 3 | Gated | Service x City | /areas/cedar-park/hail-damage-roof-repair/ | hail damage roof repair cedar park | hail damage roof repair cedar park tx | Transactional | Hail & Storm Damage Repair in Cedar Park, TX | 44 | Hail & Storm Damage Repair in Cedar Park, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/cedar-park/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P120 | 3 | Gated | Service x City | /areas/leander/roof-replacement/ | roof replacement leander | roof replacement leander tx | Transactional | Roof Replacement in Leander, TX ¦ Portillo Roofing | 50 | Roof Replacement in Leander, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/leander/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P121 | 3 | Gated | Service x City | /areas/leander/metal-roofing/ | metal roofing leander | metal roofing leander tx | Transactional | Metal Roofing in Leander, TX ¦ Portillo Roofing | 47 | Standing Seam Metal Roofing in Leander, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/leander/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P122 | 3 | Gated | Service x City | /areas/leander/hail-damage-roof-repair/ | hail damage roof repair leander | hail damage roof repair leander tx | Transactional | Hail & Storm Damage Repair in Leander, TX ¦ Portillo Roofing | 60 | Hail & Storm Damage Repair in Leander, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/leander/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
P123 | 3 | Gated | Service x City | /areas/georgetown/roof-replacement/ | roof replacement georgetown | roof replacement georgetown tx | Transactional | Roof Replacement in Georgetown, TX ¦ Portillo Roofing | 53 | Roof Replacement in Georgetown, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/georgetown/, /services/roof-replacement/, matching project | 0 | Until built, the town page owns this keyword.
P124 | 3 | Gated | Service x City | /areas/georgetown/metal-roofing/ | metal roofing georgetown | metal roofing georgetown tx | Transactional | Metal Roofing in Georgetown, TX ¦ Portillo Roofing | 50 | Standing Seam Metal Roofing in Georgetown, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/georgetown/, /services/metal-roofing/, matching project | 0 | Until built, the town page owns this keyword.
P125 | 3 | Gated | Service x City | /areas/georgetown/hail-damage-roof-repair/ | hail damage roof repair georgetown | hail damage roof repair georgetown tx | Transactional | Hail & Storm Damage Repair in Georgetown, TX | 44 | Hail & Storm Damage Repair in Georgetown, TX |  |  | A completed job of THIS service in THIS town with photos + town-specific detail. If you can't write that, don't build the page. | Service (provider #org, areaServed City) + BreadcrumbList | Completed job of this service in this town with photos | N | index | /areas/georgetown/, /services/hail-damage-roof-repair/, matching project | 0 | Until built, the town page owns this keyword.
Note on T1: Sum of Keyword Planner volume for seeds mapped to this path (and its #sections).

## Site Skeleton
Level | Surface | Path pattern | Count | Live | Draft | Planned | Section | Gated | Phase 1 | Owns cluster shape | Feeds (internal links) | Schema
0 | Home | / | 1 | 1 | 0 | 0 | 0 | 0 | 1 | roofing contractor austin | hubs, top roofing services, projects, builders | RoofingContractor + GeneralContractor (#org): foundingDate, address (Dale), telephone, areaServed [14 cities w/ Wikipedia sameAs], sameAs [GBP, BBB, Yelp, Facebook], hasOfferCatalog; WebSite
1 | Static | /about/ /contact/ /for-builders/ /for-restoration/ /reviews/ | 5 | 2 | 0 | 3 | 0 | 0 | 4 | brand; roofing subcontractor; restoration partner | projects, services | AboutPage / ContactPage / Service
1 | Hub | /services/ /projects/ /remodeling/ /countertops/ /areas/ /guides/ | 6 | 1 | 1 | 4 | 0 | 0 | 2 | category head terms | child pages | CollectionPage + BreadcrumbList
1 | Roofing service | /services/<service>/ | 13 | 0 | 0 | 12 | 0 | 1 | 7 | <service> austin | live towns, projects, guides | Service (provider #org, areaServed) + BreadcrumbList; FAQPage optional (no rich result)
1 | Trade service | /remodeling/<service>/ | 3 | 0 | 0 | 0 | 0 | 3 | 0 | <service> austin | /remodeling/, projects | Service (provider #org, areaServed) + BreadcrumbList
1 | Section | <parent>/#<service> | 18 | 0 | 0 | 0 | 18 | 0 | 0 | <service> austin (on parent page) | parent page | None of its own - listed in parent page's Service / hasOfferCatalog
2 | City | /areas/<town>/ | 13 | 0 | 0 | 2 | 0 | 11 | 2 | roofer <town>; roof repair <town> | services, projects in town, nearby towns | Service (provider #org, areaServed City) + BreadcrumbList. Never a separate business entity per town.
2 | Project | /projects/<project>/ | 10 | 0 | 9 | 0 | 0 | 1 | 5 | proof | service + town | Article/CreativeWork (contentLocation, dateCreated, about -> Service, image[]) + BreadcrumbList
2 | Guide | /guides/<question>/ | 14 | 0 | 0 | 14 | 0 | 0 | 1 | questions, costs, comparisons | matching service | Article (author Person w/ sameAs, dateModified) + BreadcrumbList
3 | Service x City | /areas/<town>/<service>/ | 39 | 0 | 0 | 1 | 0 | 38 | 0 | <service> <town> | town, service, project | Service (provider #org, areaServed City) + BreadcrumbList
9 | Utility | /thank-you/ /privacy-policy/ /terms-of-service/ | 3 | 3 | 0 | 0 | 0 | 0 | 3 | - | - | -
| Total |  | 125 | 7 | 10 | 36 | 18 | 54 | 25
Phase 1 = pages to build in the first pass (excludes Gated and Section rows; includes Live pages that get reworked).

## Services
Category | Slug | Service | Primary keyword | Lives at | Offered? (confirm) | Evidence | Phase | Status
Roofing | roof-replacement | Roof Replacement | roof replacement austin | /services/roof-replacement/ | Y | TXST Apartments (400 sq reroof) | 1 | Planned
Roofing | roof-repair | Roof Repair | roof repair austin | /services/roof-repair/ | Y | Listed on current site - need repair job photos | 1 | Planned
Roofing | metal-roofing | Standing Seam Metal Roofing | metal roofing austin | /services/metal-roofing/ | Y | Inwood, Shoalwood, Knollwood, Curved Ridges, Yuapon | 1 | Planned
Roofing | flat-roofing | Flat & TPO Roofing | tpo roofing austin | /services/flat-roofing/ | Y | Mendez School (TPO), Knollwood | 1 | Planned
Roofing | commercial-roofing | Commercial Roofing | commercial roofing austin | /services/commercial-roofing/ | Y | Travis County Jail, Mendez School, TXST, UT Batter's Eye | 1 | Planned
Roofing | new-construction-roofing | New Construction Roofing | new construction roofing austin | /services/new-construction-roofing/ | Y | Inwood, Shoalwood, Knollwood, Fiset | 1 | Planned
Roofing | hail-damage-roof-repair | Hail & Storm Damage Repair | hail damage roof repair austin | /services/hail-damage-roof-repair/ | Y | Listed on current site - need storm job photos | 1 | Planned
Roofing | shingle-roofing | Shingle Roofing | shingle roofing austin | /services/shingle-roofing/ | Y | TXST Apartments | 2 | Planned
Roofing | tile-roof-repair | Tile Roof Repair | tile roof repair austin | /services/tile-roof-repair/ | Y | Tile repair workflow (torch-down underlayment) - need photos | 2 | Planned
Roofing | roof-inspection | Roof Inspection | roof inspection austin | /services/roof-inspection/ | Y | Listed on current site | 2 | Planned
Roofing | roof-coating | Silicone & Elastomeric Roof Coating | roof coating austin | /services/roof-coating/ | ? | Owner listed 'coating' - CONFIRM roof coatings specifically | 2 | Planned
Roofing | gutters | Gutters | gutter installation austin | /services/gutters/ | ? | Travis County Jail scope included gutters - CONFIRM standalone | 3 | Planned
Roofing | emergency-roof-repair | Emergency Roof Repair | emergency roof repair austin | /services/emergency-roof-repair/ | ? | Site claims 24/7 hotline - no process confirmed | 3 | Gated
Roofing | custom-fabrication | Custom Metal Fascia & Curved Panels | custom metal fascia austin | /services/metal-roofing/#custom-fabrication | Y | Yuapon, Curved Ridges | 1 | Section
Remodeling | home-renovation | Whole-Home Interior Renovation | home renovation austin | /remodeling/home-renovation/ | Y | Villa Park (in progress), Dodd (quoted) - not proof until complete | 2 | Gated
Remodeling | patio-covers | Patio Covers & Additions | patio cover builder austin | /remodeling/patio-covers/ | Y | Huntridge (quoted) - not proof until complete | 2 | Gated
Remodeling | epoxy-flooring | Epoxy Floor & Garage Coatings | epoxy flooring austin | /remodeling/epoxy-flooring/ | Y | On relaunch branch - need finished-floor photos | 2 | Gated
Remodeling | kitchen-remodeling | Kitchen Remodeling | kitchen remodel austin | /remodeling/#kitchen | Y | Dissected from whole-home work | 2 | Section
Remodeling | bathroom-remodeling | Bathroom Remodeling | bathroom remodel austin | /remodeling/#bathroom | Y | Dissected from whole-home work | 2 | Section
Remodeling | drywall-repair | Drywall & Ceiling Repair | drywall repair austin | /remodeling/#drywall-ceiling | Y | Ceiling repair scopes; pairs with leak repairs | 2 | Section
Remodeling | tile-installation | Tile Installation | tile installation austin | /remodeling/#tile | Y | Pool waterline tile; quote system covers tile | 2 | Section
Remodeling | flooring-installation | Flooring Installation | flooring installation austin | /remodeling/#flooring | ? | CONFIRM offered standalone | 3 | Section
Remodeling | pool-tile-coping | Pool Tile & Coping | pool tile replacement austin | /remodeling/#pool-tile | ? | Pool renovation job - CONFIRM complete | 3 | Section
Remodeling | interior-painting | Interior Painting | interior painting austin | /remodeling/#interior-painting | Y | Owner confirmed painting | 2 | Section
Remodeling | exterior-painting | Exterior Painting | exterior painting austin | /remodeling/#exterior-painting | Y | Owner confirmed painting | 2 | Section
Remodeling | cabinet-painting | Cabinet Painting & Refinishing | cabinet painting austin | /remodeling/#cabinets | ? | CONFIRM offered | 3 | Section
Remodeling | deck-fence-staining | Deck & Fence Staining | fence staining austin | /remodeling/#staining | ? | CONFIRM offered - low ticket, add-on only | 3 | Section
Remodeling | house-washing | House Soft Washing | house washing austin | /remodeling/#pressure-washing | Y | Owner confirmed power washing - low ticket, add-on | 2 | Section
Remodeling | concrete-cleaning | Driveway & Concrete Cleaning | driveway cleaning austin | /remodeling/#concrete-cleaning | Y | Owner confirmed power washing - low ticket, add-on | 2 | Section
Roofing | roof-cleaning | Roof Soft Washing | roof cleaning austin | /services/roof-inspection/#roof-cleaning | ? | CONFIRM offered | 3 | Section
Countertops | granite-countertops | Granite Countertops | granite countertops austin | /countertops/#granite | Y | On relaunch branch | 2 | Section
Countertops | epoxy-countertops | Epoxy & River Countertops | epoxy countertops austin | /countertops/#epoxy-river | Y | On relaunch branch + photos | 2 | Section
Countertops | quartz-countertops | Quartz Countertops | quartz countertops austin | /countertops/#quartz | ? | CONFIRM offered | 3 | Section
Countertops | countertop-resurfacing | Countertop Resurfacing | countertop resurfacing austin | /countertops/#resurfacing | ? | CONFIRM offered | 3 | Section

## Service Areas
Slug | Town | County | Drive from Dale (min, est.) | Zone | What we take on (zone rule) | Min job size (you set) | Phase | Completed jobs here (fill in) | Pages generated | Town page status
(austin) | Austin | Travis (also Williamson, Hays) | 40 | Metro | Covered by home + service pages; no town page |  | 1 | Villa Park, Huntridge (in progress/quoted) | - | -
dale | Dale | Caldwell | 0 | South core | All services incl. add-ons |  | 1 |  | 4 | Gated - needs a job
san-marcos | San Marcos | Hays (also Caldwell/Guadalupe) | 35 | South core | All services incl. add-ons |  | 1 |  | 4 | Gated - needs a job
lockhart | Lockhart | Caldwell | 15 | South core | All services incl. add-ons |  | 2 |  | 4 | Gated - needs a job
bastrop | Bastrop | Bastrop | 30 | South core | All services incl. add-ons |  | 2 |  | 4 | Gated - needs a job
kyle | Kyle | Hays | 35 | South core | All services incl. add-ons |  | 2 |  | 4 | Gated - needs a job
buda | Buda | Hays | 40 | South core | All services incl. add-ons |  | 2 |  | 4 | Gated - needs a job
manor | Manor | Travis | 50 | East / metro | Roofing + remodeling; no low-ticket add-ons |  | 3 |  | 4 | Gated - needs a job
pflugerville | Pflugerville | Travis (also Williamson) | 55 | East / metro | Roofing + remodeling; no low-ticket add-ons |  | 3 |  | 4 | Gated - needs a job
round-rock | Round Rock | Williamson (also Travis) | 60 | North | Roofing replacement, metal, commercial, new construction only | suggested: $8k+ | 3 |  | 4 | Gated - needs a job
hutto | Hutto | Williamson | 60 | North | Roofing replacement, metal, commercial, new construction only | suggested: $8k+ | 3 |  | 4 | Gated - needs a job
cedar-park | Cedar Park | Williamson (also Travis) | 70 | North | Roofing replacement, metal, commercial, new construction only | suggested: $8k+ | 3 |  | 4 | Gated - needs a job
leander | Leander | Williamson (also Travis) | 75 | North | Roofing replacement, metal, commercial, new construction only | suggested: $8k+ | 3 |  | 4 | Gated - needs a job
georgetown | Georgetown | Williamson | 75 | North | Roofing replacement, metal, commercial, new construction only | suggested: $8k+ | 3 |  | 4 | Gated - needs a job
Drive times are off-peak estimates from Dale. Min job size is a council suggestion for north-zone towns - set your own.

## Seed Keywords
Keyword (paste into Planner) | Surface | Target path | Note | Avg monthly searches | Competition | Top-of-page bid low ($) | Top-of-page bid high ($)
roofing contractor austin | Home | /
roofing company austin | Home | /
roofers austin tx | Home | /
best roofing company austin | Home | / | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
roofers near me | GBP-driven | / | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
roofing companies near me | GBP-driven | / | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
roof repair near me | GBP-driven | /services/roof-repair/ | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
roof replacement near me | GBP-driven | /services/roof-replacement/ | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
metal roofing contractors near me | GBP-driven | /services/metal-roofing/ | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
remodeling contractors near me | GBP-driven | /remodeling/ | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
pressure washing near me | GBP-driven | /remodeling/#pressure-washing | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
countertop installers near me | GBP-driven | /countertops/ | Map-pack / GBP-driven - a page can't 'own' this; tracks demand only
roofing subcontractor austin | Static | /for-builders/
roofing subcontractor | Static | /for-builders/
restoration roofing subcontractor austin | Static | /for-restoration/
roofing services austin | Hub | /services/
remodeling contractor austin | Hub | /remodeling/
custom countertops austin | Hub | /countertops/
pressure washing austin | Section | /remodeling/#pressure-washing
power washing austin | Section | /remodeling/#pressure-washing
roof replacement austin | Roofing service | /services/roof-replacement/
roof replacement austin tx | Roofing service | /services/roof-replacement/
reroof austin | Roofing service | /services/roof-replacement/
roof replacement company austin | Roofing service | /services/roof-replacement/
new roof austin | Roofing service | /services/roof-replacement/
roof repair austin | Roofing service | /services/roof-repair/
roof repair austin tx | Roofing service | /services/roof-repair/
roof leak repair austin | Roofing service | /services/roof-repair/
roof repair company austin | Roofing service | /services/roof-repair/
metal roofing austin | Roofing service | /services/metal-roofing/
metal roofing austin tx | Roofing service | /services/metal-roofing/
standing seam metal roof austin | Roofing service | /services/metal-roofing/
metal roof contractor austin | Roofing service | /services/metal-roofing/
custom metal fascia | Roofing service | /services/metal-roofing/
curved standing seam panels | Roofing service | /services/metal-roofing/
tpo roofing austin | Roofing service | /services/flat-roofing/
tpo roofing austin tx | Roofing service | /services/flat-roofing/
flat roof repair austin | Roofing service | /services/flat-roofing/
flat roof replacement austin | Roofing service | /services/flat-roofing/
commercial roofing austin | Roofing service | /services/commercial-roofing/
commercial roofing austin tx | Roofing service | /services/commercial-roofing/
commercial roofing contractor austin | Roofing service | /services/commercial-roofing/
commercial roof replacement austin | Roofing service | /services/commercial-roofing/
commercial tpo contractor | Roofing service | /services/commercial-roofing/
new construction roofing austin | Roofing service | /services/new-construction-roofing/
new construction roofing austin tx | Roofing service | /services/new-construction-roofing/
builder roofing contractor austin | Roofing service | /services/new-construction-roofing/
new home roofing austin | Roofing service | /services/new-construction-roofing/
hail damage roof repair austin | Roofing service | /services/hail-damage-roof-repair/
hail damage roof repair austin tx | Roofing service | /services/hail-damage-roof-repair/
storm damage roof repair austin | Roofing service | /services/hail-damage-roof-repair/
hail damage roof inspection | Roofing service | /services/hail-damage-roof-repair/
wind damage roof repair | Roofing service | /services/hail-damage-roof-repair/
insurance roof inspection austin | Roofing service | /services/hail-damage-roof-repair/
shingle roofing austin | Roofing service | /services/shingle-roofing/
shingle roofing austin tx | Roofing service | /services/shingle-roofing/
asphalt shingle roof austin | Roofing service | /services/shingle-roofing/
architectural shingles austin | Roofing service | /services/shingle-roofing/
impact resistant shingles austin | Roofing service | /services/shingle-roofing/
tile roof repair austin | Roofing service | /services/tile-roof-repair/
tile roof repair austin tx | Roofing service | /services/tile-roof-repair/
clay tile roof repair austin | Roofing service | /services/tile-roof-repair/
concrete tile roof repair | Roofing service | /services/tile-roof-repair/
roof inspection austin | Roofing service | /services/roof-inspection/
roof inspection austin tx | Roofing service | /services/roof-inspection/
free roof inspection austin | Roofing service | /services/roof-inspection/
roof inspection for home sale | Roofing service | /services/roof-inspection/
roof coating austin | Roofing service | /services/roof-coating/
roof coating austin tx | Roofing service | /services/roof-coating/
silicone roof coating austin | Roofing service | /services/roof-coating/
elastomeric roof coating | Roofing service | /services/roof-coating/
flat roof coating austin | Roofing service | /services/roof-coating/
gutter installation austin | Roofing service | /services/gutters/
gutter installation austin tx | Roofing service | /services/gutters/
seamless gutters austin | Roofing service | /services/gutters/
gutter replacement austin | Roofing service | /services/gutters/
emergency roof repair austin | Roofing service | /services/emergency-roof-repair/
emergency roof repair austin tx | Roofing service | /services/emergency-roof-repair/
roof tarp service austin | Roofing service | /services/emergency-roof-repair/
24 hour roofer austin | Roofing service | /services/emergency-roof-repair/
home renovation austin | Trade service | /remodeling/home-renovation/
whole house remodel austin | Trade service | /remodeling/home-renovation/
interior renovation contractor austin | Trade service | /remodeling/home-renovation/
patio cover builder austin | Trade service | /remodeling/patio-covers/
covered patio addition austin | Trade service | /remodeling/patio-covers/
patio roof austin | Trade service | /remodeling/patio-covers/
epoxy flooring austin | Trade service | /remodeling/epoxy-flooring/
garage floor coating austin | Trade service | /remodeling/epoxy-flooring/
epoxy garage floor austin | Trade service | /remodeling/epoxy-flooring/
polyaspartic floor coating | Trade service | /remodeling/epoxy-flooring/
kitchen remodel austin | Section | /remodeling/#kitchen
kitchen remodeling contractor austin | Section | /remodeling/#kitchen
bathroom remodel austin | Section | /remodeling/#bathroom
shower remodel austin | Section | /remodeling/#bathroom
drywall repair austin | Section | /remodeling/#drywall-ceiling
ceiling repair austin | Section | /remodeling/#drywall-ceiling
water damage drywall repair austin | Section | /remodeling/#drywall-ceiling
tile installation austin | Section | /remodeling/#tile
bathroom tile installer austin | Section | /remodeling/#tile
backsplash installation austin | Section | /remodeling/#tile
flooring installation austin | Section | /remodeling/#flooring
vinyl plank flooring installation austin | Section | /remodeling/#flooring
pool tile replacement austin | Section | /remodeling/#pool-tile
pool coping replacement austin | Section | /remodeling/#pool-tile
interior painting austin | Section | /remodeling/#interior-painting
interior painters austin | Section | /remodeling/#interior-painting
exterior painting austin | Section | /remodeling/#exterior-painting
exterior house painters austin | Section | /remodeling/#exterior-painting
house painters austin | Section | /remodeling/#exterior-painting
cabinet painting austin | Section | /remodeling/#cabinets
kitchen cabinet refinishing austin | Section | /remodeling/#cabinets
fence staining austin | Section | /remodeling/#staining
deck staining austin | Section | /remodeling/#staining
house washing austin | Section | /remodeling/#pressure-washing
soft wash house austin | Section | /remodeling/#pressure-washing
driveway cleaning austin | Section | /remodeling/#concrete-cleaning
concrete cleaning austin | Section | /remodeling/#concrete-cleaning
patio pressure washing austin | Section | /remodeling/#concrete-cleaning
roof cleaning austin | Section | /services/roof-inspection/#roof-cleaning
roof soft wash austin | Section | /services/roof-inspection/#roof-cleaning
granite countertops austin | Section | /countertops/#granite
granite countertop installation austin | Section | /countertops/#granite
epoxy countertops austin | Section | /countertops/#epoxy-river
river table countertop | Section | /countertops/#epoxy-river
live edge epoxy countertop austin | Section | /countertops/#epoxy-river
quartz countertops austin | Section | /countertops/#quartz
quartz countertop installation austin | Section | /countertops/#quartz
countertop resurfacing austin | Section | /countertops/#resurfacing
epoxy countertop over laminate | Section | /countertops/#resurfacing
custom metal fascia austin | Section | /services/metal-roofing/#custom-fabrication
curved standing seam roof | Section | /services/metal-roofing/#custom-fabrication
tapered metal fascia | Section | /services/metal-roofing/#custom-fabrication
roofer dale | City | /areas/dale/
roofing company dale | City | /areas/dale/
roofing contractor dale tx | City | /areas/dale/
roof repair dale | City | /areas/dale/
roof replacement dale | Service x City | /areas/dale/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing dale | Service x City | /areas/dale/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair dale | Service x City | /areas/dale/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer san marcos | City | /areas/san-marcos/
roofing company san marcos | City | /areas/san-marcos/
roofing contractor san marcos tx | City | /areas/san-marcos/
roof repair san marcos | City | /areas/san-marcos/
roof replacement san marcos | Service x City | /areas/san-marcos/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing san marcos | Service x City | /areas/san-marcos/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair san marcos | Service x City | /areas/san-marcos/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer lockhart | City | /areas/lockhart/
roofing company lockhart | City | /areas/lockhart/
roofing contractor lockhart tx | City | /areas/lockhart/
roof repair lockhart | City | /areas/lockhart/
roof replacement lockhart | Service x City | /areas/lockhart/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing lockhart | Service x City | /areas/lockhart/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair lockhart | Service x City | /areas/lockhart/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer bastrop | City | /areas/bastrop/
roofing company bastrop | City | /areas/bastrop/
roofing contractor bastrop tx | City | /areas/bastrop/
roof repair bastrop | City | /areas/bastrop/
roof replacement bastrop | Service x City | /areas/bastrop/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing bastrop | Service x City | /areas/bastrop/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair bastrop | Service x City | /areas/bastrop/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer kyle | City | /areas/kyle/
roofing company kyle | City | /areas/kyle/
roofing contractor kyle tx | City | /areas/kyle/
roof repair kyle | City | /areas/kyle/
roof replacement kyle | Service x City | /areas/kyle/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing kyle | Service x City | /areas/kyle/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair kyle | Service x City | /areas/kyle/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer buda | City | /areas/buda/
roofing company buda | City | /areas/buda/
roofing contractor buda tx | City | /areas/buda/
roof repair buda | City | /areas/buda/
roof replacement buda | Service x City | /areas/buda/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing buda | Service x City | /areas/buda/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair buda | Service x City | /areas/buda/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer manor | City | /areas/manor/
roofing company manor | City | /areas/manor/
roofing contractor manor tx | City | /areas/manor/
roof repair manor | City | /areas/manor/
roof replacement manor | Service x City | /areas/manor/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing manor | Service x City | /areas/manor/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair manor | Service x City | /areas/manor/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer pflugerville | City | /areas/pflugerville/
roofing company pflugerville | City | /areas/pflugerville/
roofing contractor pflugerville tx | City | /areas/pflugerville/
roof repair pflugerville | City | /areas/pflugerville/
roof replacement pflugerville | Service x City | /areas/pflugerville/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing pflugerville | Service x City | /areas/pflugerville/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair pflugerville | Service x City | /areas/pflugerville/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer round rock | City | /areas/round-rock/
roofing company round rock | City | /areas/round-rock/
roofing contractor round rock tx | City | /areas/round-rock/
roof repair round rock | City | /areas/round-rock/
roof replacement round rock | Service x City | /areas/round-rock/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing round rock | Service x City | /areas/round-rock/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair round rock | Service x City | /areas/round-rock/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer hutto | City | /areas/hutto/
roofing company hutto | City | /areas/hutto/
roofing contractor hutto tx | City | /areas/hutto/
roof repair hutto | City | /areas/hutto/
roof replacement hutto | Service x City | /areas/hutto/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing hutto | Service x City | /areas/hutto/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair hutto | Service x City | /areas/hutto/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer cedar park | City | /areas/cedar-park/
roofing company cedar park | City | /areas/cedar-park/
roofing contractor cedar park tx | City | /areas/cedar-park/
roof repair cedar park | City | /areas/cedar-park/
roof replacement cedar park | Service x City | /areas/cedar-park/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing cedar park | Service x City | /areas/cedar-park/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair cedar park | Service x City | /areas/cedar-park/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer leander | City | /areas/leander/
roofing company leander | City | /areas/leander/
roofing contractor leander tx | City | /areas/leander/
roof repair leander | City | /areas/leander/
roof replacement leander | Service x City | /areas/leander/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing leander | Service x City | /areas/leander/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair leander | Service x City | /areas/leander/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roofer georgetown | City | /areas/georgetown/
roofing company georgetown | City | /areas/georgetown/
roofing contractor georgetown tx | City | /areas/georgetown/
roof repair georgetown | City | /areas/georgetown/
roof replacement georgetown | Service x City | /areas/georgetown/roof-replacement/ | Town page owns this until the matrix page is built
metal roofing georgetown | Service x City | /areas/georgetown/metal-roofing/ | Town page owns this until the matrix page is built
hail damage roof repair georgetown | Service x City | /areas/georgetown/hail-damage-roof-repair/ | Town page owns this until the matrix page is built
roof replacement cost austin | Guide | /guides/roof-replacement-cost-austin/
new roof cost austin | Guide | /guides/roof-replacement-cost-austin/
cost per square roofing austin | Guide | /guides/roof-replacement-cost-austin/
metal roof cost austin | Guide | /guides/metal-roof-cost-austin/
standing seam metal roof cost per square foot texas | Guide | /guides/metal-roof-cost-austin/
metal vs shingle roof texas | Guide | /guides/metal-vs-shingle-roof-texas/
is a metal roof worth it in texas | Guide | /guides/metal-vs-shingle-roof-texas/
best roof for texas heat | Guide | /guides/metal-vs-shingle-roof-texas/
does insurance cover hail damage roof texas | Guide | /guides/does-insurance-cover-hail-damage-texas/
hail damage roof claim process texas | Guide | /guides/does-insurance-cover-hail-damage-texas/
signs of hail damage on roof | Guide | /guides/signs-of-hail-damage-on-roof/
what does hail damage look like on shingles | Guide | /guides/signs-of-hail-damage-on-roof/
hail damage metal roof | Guide | /guides/signs-of-hail-damage-on-roof/
how long does a roof last in texas | Guide | /guides/how-long-does-a-roof-last-in-texas/
shingle roof lifespan texas | Guide | /guides/how-long-does-a-roof-last-in-texas/
metal roof lifespan | Guide | /guides/how-long-does-a-roof-last-in-texas/
standing seam vs exposed fastener metal roof | Guide | /guides/standing-seam-vs-exposed-fastener/
snap lock vs mechanical lock standing seam | Guide | /guides/standing-seam-vs-exposed-fastener/
tile roof underlayment replacement cost | Guide | /guides/tile-roof-repair-vs-replacement/
tile roof underlayment replacement | Guide | /guides/tile-roof-repair-vs-replacement/
reuse roof tiles | Guide | /guides/tile-roof-repair-vs-replacement/
tpo vs modified bitumen | Guide | /guides/tpo-vs-modified-bitumen/
best flat roof material texas | Guide | /guides/tpo-vs-modified-bitumen/
roofing permit austin | Guide | /guides/roofing-permit-austin/
city of austin reroof permit | Guide | /guides/roofing-permit-austin/
how to choose a roofer austin | Guide | /guides/how-to-choose-a-roofer-austin/
roofing scams after hail storm texas | Guide | /guides/how-to-choose-a-roofer-austin/
how long does a roof replacement take | Guide | /guides/roof-replacement-timeline/
roof replacement process | Guide | /guides/roof-replacement-timeline/
granite vs epoxy countertops | Guide | /guides/granite-vs-epoxy-countertops/
epoxy countertop durability | Guide | /guides/granite-vs-epoxy-countertops/
home renovation cost austin | Guide | /guides/home-renovation-cost-austin/
cost to gut and remodel a house austin | Guide | /guides/home-renovation-cost-austin/

## Off-site Entity
Priority | Item | Action | Why | Status
1 | Google Business Profile | Primary category Roofing contractor; add General contractor only if provable; Services list mirrors roofing pages; service areas = 14 towns (within 2-hr limit); hide address if customers don't visit | Primary category is the top local-pack factor; proximity to Dale limits map-pack reach in north metro.
2 | Review process | Same-day review request at every job close (incl. GCs); ask them to mention the service + town in their own words; never incentivize or script | Review volume/recency drives map pack + AI picks.
3 | Bing Places | Import from GBP; verify | ChatGPT local results lean on Bing data.
4 | NAP consistency | Identical name / phone (512) 629-1342 / location line on site, GBP, Bing, BBB, Yelp, Facebook, Nextdoor | Entity consistency.
5 | Yelp, BBB, Facebook | Complete profiles with real project photos | Perplexity/ChatGPT cite these listings heavily.
6 | Angi + Thumbtack (free profiles) | Claim free profiles; don't buy leads | Appear in AI citations for home services.
7 | Apple Business Connect | Claim listing | Cheap, feeds Apple Maps/Siri.
8 | Manufacturer / supplier directories | Ask suppliers (e.g., McElroy dealer network) about installer listings | Authoritative backlinks + citations.
9 | GC / builder partner links | Ask builders to link the project page for their job | Relevant local links.
10 | Local press | Pitch Travis County Jail + UT Batter's Eye stories to local outlets | Prominence + AI-citable third-party mention.
11 | Chambers of commerce | Bastrop, Lockhart, Kyle (south-core zone) | Local citations where map-pack wins are realistic.
12 | Monthly AI baseline | Run the 'AI Baseline' tab prompts on the 1st of each month; record cited Y/N | Only way to know if any of this works.
13 | Proof workflow (crew lead, ~10 min/job) | Before: 6 photos (4 elevations, problem close-up, street sign). During: 4 (tear-off, deck/underlayment, flashing, crew). After: 6 same angles + 1 wide. Folder YYYY-MM_town_service_lastname. Marco: 5-line card (town, scope, squares/material, ticket range, problem->fix). Update Service Areas 'Completed jobs' monthly - that's what un-gates town pages. | Proof is the bottleneck for every gated page.

## AI Baseline
# | Prompt (run in ChatGPT, Gemini, Google AI Mode, Perplexity) | Oct 2026 cited in # of 4 | Nov 2026 cited in # of 4 | Dec 2026 cited in # of 4 | Jan 2027 cited in # of 4 | Feb 2027 cited in # of 4 | Mar 2027 cited in # of 4
1 | best roofer in Austin TX
2 | who installs standing seam metal roofs in Austin
3 | roofing contractor near Dale TX
4 | roofer in Lockhart TX
5 | roofer in Bastrop TX
6 | roofer in San Marcos TX
7 | roofer in Kyle TX
8 | commercial TPO roofing contractor Austin
9 | roofing subcontractor for home builders Austin
10 | hail damage roof repair Austin
11 | how much does a roof replacement cost in Austin
12 | custom curved metal roof panels Texas
13 | family owned roofing company Central Texas
14 | epoxy countertops Austin
15 | remodeling contractor Bastrop TX
| Total citations (max 60) | 0 | 0 | 0 | 0 | 0 | 0

## Council Log
Seat | Verdict | Key findings | What was done
Local SEO | Approve with changes | Gate city pages too; town page owns 'roof repair <town>' (so no repair matrix pages); collapse trade hubs; fix cannibalization; Phase 1 ~22 pages; off-site work > pages | Adopted (cities gated; Dale + San Marcos lead; hubs collapsed; conflicts removed; Phase 1 cut)
AI search | Approve with changes | AI answers come from Bing/GBP/Yelp/BBB, not your site alone; JS portfolio invisible to crawlers; schema small + correct; required-fact copy fields | Adopted (Off-site tab, AI Baseline tab, static project pages, schema fixes, Copy column)
Owner economics | Approve with changes | Roofing first; low-ticket trades as add-ons; Phase 1 ~22; cities by drive time from Dale; add /for-restoration/ | Adopted. Partly overridden: kept all trades you named as sections on /remodeling/ instead of cutting them
Red team | Approve with changes | Competitor photos + fake testimonials on live site; insurance copy breaks Tex. Ins. Code 4102.163; unsourced claims; placeholders | Adopted - verified in repo + TDI; moved to Phase 0 tab
Disagreement | - | Merge Commercial + Flat/TPO pages? (economics: yes; SEO: no) | Kept separate - different buyers; revisit with Planner data
Disagreement | - | Cut pressure washing/staining entirely (economics) vs. keep (owner said offered) | Kept as sections on /remodeling/ with zone limits - your call